## Model
To run a Monte Carlo simulation, select "Run Simulation" from the Monte Carlo tab.
Project Model |  |  |  |  | Simulation Statistics
| Best-Case | Expected | Worst-Case | Sample (PERT) | Min | Average | Max
Task 1 | 10 | 20 | 30 | 17 | 11 | 19.999 | 29
Task 2 | 10 | 20 | 30 | 14 | 11 | 20.003 | 30
Task 3 | 5 | 10 | 20 | 11 | 5 | 10.835 | 19
Total | 25 | 50 | 80 | 42 | 30 | 50.837 | 69
Analysis
Probability of Completion |  |  | Days | Probability
| within Expected |  | 50 | 48.6%
| within Expected + 10% |  | 55 | 78.2%
| within Expected + 20% |  | 60 | 93.3%
Confidence Levels
| 75% |  | 55
| 85% |  | 57

## Charts
Chart Data
Value | Cumulative | Target
32 | 0.1% | 0.1%
34 | 0.4% | 0.3%
36 | 1% | 0.9%
38 | 2.1% | 1.5%
40 | 4.5% | 2.9%
42 | 8% | 5.2%
44 | 15.6% | 9.6%
46 | 24.4% | 12.4%
48 | 35% | 15.8%
50 | 48.6% | 19%
52 | 60.7% | 18.6%
54 | 73.3% | 18.3%
56 | 83.4% | 15.9%
58 | 88.5% | 10.3%
60 | 93.3% | 7.3%
62 | 96.5% | 5.1%
64 | 98.3% | 3.4%
66 | 99.5% | 2.2%
68 | 99.9% | 0.9%
70 | 100% | 0.3%
72 | 100% | 0%